## Unbalnce
Engineering Dept.-PMCI Devision
Electrical PM PLAN for Unbalnce machine for Year2026
Machine | NO. | Task Description | Task Code | Estimated Time (MIN) | Crew | Period (week) | Weeks
 | time axis 2025-12-31 to 2026-12-23
 | time axis 2025-12-31 to 2026-12-23
Unbalance | 1 | Check the function of relays,fuses&power contacors. | Un18 | 90 | 1 | 52
| 2 | Check the grease of cardan drive shafts. | Un19 | 30 | 1 | 52
| 3 | Check &grease bearing of motor | Un20 | 60 | 1 | 16
| 4 | Check pressure container sealing. | Un21 | 90 | 1 | 8
| 5 | clean cooling air paths. | Un22 | 60 | 1 | 8
| 6 | check the shaft sealing ring | Un23 | 60 | 1 | 8
| 7 | Check &replace motor ball bearing | Un24 | 45 | 1 | 16
Issued: | [6 empty] | 2026-01-21: Reviewed:; 2026-07-08: Approved:; 2026-10-28: Issue:
Date: 30-12-2025
page:1/1

## Unifomaty
Engineering Dept.-PMCI Devision
Electrical PM PLAN for UNIFORMITY machine for Year2026
Machine | NO. | Task Description | Task Code | Estimated Time (MIN) | Crew | Period (week) | Weeks
 | time axis 2025-12-31 to 2026-12-23
 | time axis 2025-12-31 to 2026-12-23
Uniformity | 1 | Checking the Mech. Movement of the relay and replacement if needed. | 3.1 | 60 | 1 | 12
| 2 | Checking and reconnecting wires | 3.2 | 60 | 1 | 12
| 3 | Cleaning the Panel with blower | 4.1 | 30 | 1 | 12
| 4 | Checking all Panel components ( control and Power ) [ C.B, Contactors, Relays, …] | 4.2 | 60 | 1 | 12
| 5 | Checking cables condition from and to the panel | 4.3 | 20 | 1 | 12
| 6 | Connecting and fixing PLC modules | 4.4 | 10 | 1 | 12
| 7 | Cleaning PLC modules using spray | 5.1 | 10 | 1 | 12
| 8 | Checking working of Air condition | 5.2 | 10 | 1 | 12
| 9 | Testing all selectors Movements | 6.1 | 10 | 1 | 12
| 10 | Rewiring the selector and replacement for defected | 12.1 | 10 | 1 | 12
| 11 | Testing the probes positions | 12.3 | 20 | 1 | 12
| 12 | Measuring Chuck width | 14 | 90 | 1 | 12
| 13 | Testing motor and brushes | 15 | 90 | 1 | 12
| 14 | Testing all safety sensors | 16 | 60 | 1 | 12
| 15 | Fixing LS arms | 17 | 60 | 1 | 12
| 16 | setting for safety relays | 11.1 | 60 | 1 | 12
| 17 | setting and cleaning sensors | 11.2 | 30 | 1 | 12
ISSUED : Ahmed Mosaad | [6 empty] | 2026-01-21: Reviewed:; 2026-07-08: Approved:; 2026-10-28: Issue:
Date:30-12-2025
page:1/1