## Inspection_Mechanical_PM_Plan
Machine | Sub_Machine | . | Task_Description | Task_Code | Estimated_mins | Crew | Period_freq | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
Buffing Machine | Buffing Machine | 1 | check air setting (air regulators & filter) | X1 | 60 | 1M | 16 | bar: W4; W20; W36; W52
Buffing Machine | Buffing Machine | 2 | check and inspect air cylinders. | X9 | 60 | 1M | 16 | bar: W4; W20; W36; W52
Buffing Machine | Buffing Machine | 3 | check tightness for bolts &coupling. | X10 | 30 | 1M | 16 | bar: W4; W20; W36; W52
Buffing Machine | Buffing Machine | 4 | check pneuamtic system of the operation (solenoid valves). | X9 | 60 | 1M | 16 | bar: W4; W20; W36; W52
Buffing Machine | Buffing Machine | 5 | Check gear boxes oil leakage | X5 | 20 | 1M | 16 | bar: W4; W20; W36; W52
Buffing Machine | Buffing Machine | 6 | Change oil leakage | X5 | 10 | 1M | 52 | bar: W4
Buffing Machine | Buffing Machine | 7 | Check greasing points | X5 | 40 | 1M | 16 | bar: W4; W20; W36; W52
Conveyor System |  | 1 | clean,lubricateall sprocket&chain. | C1 | 180 | 1M | 16 | bar: W3; W19; W35; W51
Conveyor System |  | 2 | check the tension of all chain of turn tables. | C2 | 90 | 1M | 16 | bar: W3; W19; W35; W51
Conveyor System |  | 3 | check the tightness for mounting bolts. | C3 | 90 | 1M | 8 | bar: W3; W11; W19; W27; W35; W43; W51
Conveyor System |  | 4 | check tension or all bolts. | C4 | 180 | 1M | 16 | bar: W3; W19; W35; W51
Conveyor System |  | 5 | inspect&clean for rollers and pulleys. | C5 | 240 | 1M | 52 | bar: W24
Conveyor System |  | 6 | check operation of air actuator. | C6 | 120 | 1M | 4 | bar: W3; W7; W11; W15; W19; W23; W27; W31; W35; W39; W43; W47; W51
Conveyor System |  | 7 | check,clean the tannel belt from dirty and dust | C7 | 180 | 1M | 12 | bar: W16; W28; W40; W52
Conveyor System |  | 8 | check ,clean the belt before elevato from dirty | C8 | 180 | 1M | 12 | bar: W3; W15; W27; W39; W51
Conveyor System |  | 9 | check the chain tension of elevator. | C9 | 120 | 1M | 26 | bar: W12; W38
Conveyor System |  | 10 | check the condition of gate of unloading conveor. | C10 | 300 | 1M | 8 | bar: W3; W11; W19; W27; W35; W43; W51
Conveyor System |  | 11 | inspect,cleanfor air &pneumatic system. | C11 | 90 | 1M | 16 | bar: W2; W18; W34; W50
Conveyor System |  | 12 | inspect&clean for all gearboxes. | C12 | 90 | 1M | 26 | bar: W12; W38
Conveyor System |  | 13 | insppect&clean for all rollers brakes. | C13 | 240 | 1M | 16 | bar: W2; W18; W34; W50
Mould Clean Machine |  | 1 | check, clean&inspect racks and gear box | M1 | 120 | 1M | 13 | bar: W4; W17; W30; W43
Mould Clean Machine |  | 2 | check tightness of all chains | M2 | 90 | 1M | 13 | bar: W4; W17; W30; W43
Mould Clean Machine |  | 3 | check and inspect steam lines and mechaical connections. | M3 | 180 | 1M | 13 | bar: W4; W17; W30; W43
Mould Clean Machine |  | 4 | check oil for gear box and air lubractor | M4 | 60 | 1M | 13 | bar: W4; W17; W30; W43
Mould Clean Machine |  | 5 | check and inspect liquid nozzles | M5 | 150 | 1M | 26 | bar: W4; W30
Mould Clean Machine |  | 6 | check wear for moving parts. | M6 | 180 | 1M | 13 | bar: W4; W17; W30; W43
Mould Clean Machine |  | 7 | check and inspect main pump. | M7 | 210 | 1M | 26 | bar: W4; W30
Mould Clean Machine |  | 8 | check and inspect Dosing chemical pump. | M8 | 120 | 1M | 26 | bar: W4; W30
Mould Clean Machine |  | 9 | check and inspect operation of machinedoor. | M10 | 150 | 1M | 8 | bar: W4; W12; W20; W28; W36; W44; W52
Mould Clean Machine |  | 10 | check operation of steam safety valve. | M11 | 120 | 1M | 8 | bar: W4; W12; W20; W28; W36; W44; W52
Mould Clean Machine |  | 11 | check operation of water tank wih level control(float) | M12 | 120 | 1M | 13 | bar: W4; W17; W30; W43
Mould Clean Machine |  | 12 | check all pneumatic control | M13 | 150 | 1M | 26 | bar: W3; W29
Repair Machines |  | 1 | clean and lubrcate all moving parts. | R1 | 180 | 1M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
Repair Machines |  | 2 | check and grease all nipples | R2 | 180 | 1M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
Repair Machines |  | 3 | check oil level for air lubrcator. | R3 | 90 | 1M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
Repair Machines |  | 4 | check for any leakage for air | R4 | 240 | 1M | 4 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
Repair Machines |  | 5 | check for any leakage for oil | R5 | 120 | 1M | 4 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
Repair Machines |  | 6 | check tightness for all bolts and moving parts. | R6 | 300 | 1M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
Repair Machines |  | 7 | check the operation of all pneumatic motions (speed) | R7 | 180 | 1M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
Repair Machines |  | 8 | check the condition of operation for air cylinders | R7 | 180 | 1M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
Repair Machines |  | 9 | check the operation of all air Solenoid valves | R7 | 180 | 1M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
Test tire M/C 3 |  | 1 | Check AC motor running status | 3.1 | 60 | 1E | 26 | bar: W1; W27
Test tire M/C 3 |  | 2 | Check wear condition and tautness of V-belts | 3.2 | 60 | 1E | 26 | bar: W1; W27
Test tire M/C 3 |  | 3 | Check the firmness of small belt pulley | 4.1 | 30 | 1E | 52 | bar: W1
Test tire M/C 3 |  | 4 | Check the firmness of large belt pulley | 4.2 | 60 | 1E | 52 | bar: W1
Test tire M/C 3 |  | 5 | Check oil cylinder | 4.3 | 20 | 1E | 52 | bar: W1
Test tire M/C 3 |  | 6 | Check drum shaft bearing | 4.4 | 10 | 1E | 26 | bar: W1; W27
Test tire M/C 3 |  | 7 | Check spindle back bearing | 5.1 | 10 | 1E | 26 | bar: W1; W27
Test tire M/C 3 |  | 8 | Check spindle front bearing | 5.2 | 10 | 1E | 26 | bar: W1; W27
Test tire M/C 3 |  | 9 | Check pneumatic disc brake | 6.1 | 10 | 1E | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
Test tire M/C 3 |  | 10 | Check limit switch of anti-blowout system | 12.1 | 10 | 1E | 52 | bar: W1
Test tire M/C 3 |  | 11 | Check connecting rod of anti-blowout system | 12.3 | 20 | 1E | 1 | bar: W1 to W52
Test tire M/C 3 |  | 12 | Check safety pin of anti-blowout system | 16 | 60 | 1E | 1 | bar: W1 to W52
Test tire M/C 3 |  | 13 | Check deflation and retraction limit switches | 17 | 60 | 1E | 52 | bar: W1
Test tire M/C 3 |  | 14 | Check linear guide | 11.1 | 60 | 1E | 52 | bar: W1
Test tire M/C 3 |  | 15 | Check air supply treatment device | 11.2 | 30 | 1E | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
Test tire M/C 4 |  | 1 | Check AC motor running status | 3.1 | 60 | 1E | 26 | bar: W1; W27
Test tire M/C 4 |  | 2 | Check wear condition and tautness of V-belts | 3.2 | 60 | 1E | 26 | bar: W1; W27
Test tire M/C 4 |  | 3 | Check the firmness of small belt pulley | 4.1 | 30 | 1E | 52 | bar: W1
Test tire M/C 4 |  | 4 | Check the firmness of large belt pulley | 4.2 | 60 | 1E | 52 | bar: W1
Test tire M/C 4 |  | 5 | Check oil cylinder | 4.3 | 20 | 1E | 52 | bar: W1
Test tire M/C 4 |  | 6 | Check drum shaft bearing | 4.4 | 10 | 1E | 26 | bar: W1; W27
Test tire M/C 4 |  | 7 | Check spindle back bearing | 5.1 | 10 | 1E | 26 | bar: W1; W27
Test tire M/C 4 |  | 8 | Check spindle front bearing | 5.2 | 10 | 1E | 26 | bar: W1; W27
Test tire M/C 4 |  | 9 | Check pneumatic disc brake | 6.1 | 10 | 1E | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
Test tire M/C 4 |  | 10 | Check limit switch of anti-blowout system | 12.1 | 10 | 1E | 52 | bar: W1
Test tire M/C 4 |  | 11 | Check connecting rod of anti-blowout system | 12.3 | 20 | 1E | 1 | bar: W1 to W52
Test tire M/C 4 |  | 12 | Check safety pin of anti-blowout system | 16 | 60 | 1E | 1 | bar: W1 to W52
Test tire M/C 4 |  | 13 | Check deflation and retraction limit switches | 17 | 60 | 1E | 52 | bar: W1
Test tire M/C 4 |  | 14 | Check linear guide | 11.1 | 60 | 1E | 52 | bar: W1
Test tire M/C 4 |  | 15 | Check air supply treatment device | 11.2 | 30 | 1E | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
Test Wheel 1 |  | 1 | check tracking ,tension and wear for drive belt. | T1 | 90 | 1M | 13 | bar: W5; W18; W31; W44
Test Wheel 1 |  | 2 | clean side ways fo carriage. | T2 | 120 | 1M | 13 | bar: W5; W18; W31; W44
Test Wheel 1 |  | 3 | grease bearing for DC and pump motor. | T3 | 90 | 1M | 26 | bar: W5; W31
Test Wheel 1 |  | 4 | gearse bearing for load wheel and spindle. | T4 | 150 | 1M | 26 | bar: W5; W31
Test Wheel 1 |  | 5 | make tension test for drive belt. | T5 | 180 | 1M | 26 | bar: W5; W31
Test Wheel 1 |  | 6 | check wear for carriage slide ways. | T6 | 180 | 1M | 26 | bar: W5; W31
Test Wheel 1 |  | 7 | remove load wheel for cleaning and errrcting a | T7 | 2160 | 1M | 52 | bar: W22
Test Wheel 1 |  | 8 | remove spindle for cleaning and errecting gain. | T8 | 1920 | 1M | 52 | bar: W40
Test Wheel 2 |  | 1 | check tracking ,tension and wear for drive belt. | T1 | 90 | 1M | 13 | bar: W5; W18; W31; W44
Test Wheel 2 |  | 2 | clean side ways fo carriage. | T2 | 120 | 1M | 13 | bar: W5; W18; W31; W44
Test Wheel 2 |  | 3 | grease bearing for DC and pump motor. | T3 | 90 | 1M | 26 | bar: W5; W31
Test Wheel 2 |  | 4 | gearse bearing for load wheel and spindle. | T4 | 150 | 1M | 26 | bar: W5; W31
Test Wheel 2 |  | 5 | make tension test for drive belt. | T5 | 180 | 1M | 26 | bar: W5; W31
Test Wheel 2 |  | 6 | check wear for carriage slide ways. | T6 | 180 | 1M | 26 | bar: W5; W31
Test Wheel 2 |  | 7 | remove load wheel for cleaning and errrcting a | T7 | 2160 | 1M | 52 | bar: W22
Test Wheel 2 |  | 8 | remove spindle for cleaning and errecting gain. | T8 | 1920 | 1M | 52 | bar: W40
UNIFORMITY |  | 1 | clean and lubricte for asam unit parts. | U1 | 90 | 1M | 8 | bar: W5; W13; W21; W29; W37; W45
UNIFORMITY |  | 2 | check oil level for air lubrcation. | U2 | 30 | 1M | 8 | bar: W5; W13; W21; W29; W37; W45
UNIFORMITY |  | 3 | check wear and grease for slide ways. | U3 | 60 | 1M | 8 | bar: W5; W13; W21; W29; W37; W45
UNIFORMITY |  | 4 | clean the load wheel. | U4 | 90 | 1M | 8 | bar: W5; W13; W21; W29; W37; W45
UNIFORMITY |  | 5 | check the setting for air and oil regulators. | U5 | 60 | 1M | 13 | bar: W8; W21; W34; W47
UNIFORMITY |  | 6 | check leaks for air and oil system. | U6 | 60 | 1M | 13 | bar: W8; W21; W34; W47
UNIFORMITY |  | 7 | check, clean and drin for air filters. | U7 | 45 | 1M | 13 | bar: W8; W21; W34; W47
UNIFORMITY |  | 8 | check pop up filter (hydraulic unit) | U8 | 45 | 1M | 13 | bar: W8; W21; W34; W47
UNIFORMITY |  | 9 | check oil level for gearbox. | U9 | 30 | 1M | 13 | bar: W8; W21; W34; W47
UNIFORMITY |  | 10 | check tightness for all chains. | U10 | 90 | 1M | 26 | bar: W12; W38
UNIFORMITY |  | 11 | check tightness for all bolts and couplings. | U11 | 180 | 1M | 26 | bar: W13; W39
UNIFORMITY |  | 12 | check and inspect for all timing belt. | U12 | 90 | 1M | 26 | bar: W14; W40
UNIFORMITY |  | 13 | check wear for guides ,screwa and gears. | U13 | 180 | 1M | 26 | bar: W15; W41
UNIFORMITY |  | 14 | check oil and clean the filter of hydraulic unit. | U14 | 60 | 1M | 26 | bar: W16; W42
UNIFORMITY |  | 15 | inspect and clean all conveyors. | U15 | 180 | 1M | 52 | bar: W2
UNIFORMITY |  | 16 | inspect and check for pneumatic system. | U16 | 90 | 1M | 52 | bar: W2
UNIFORMITY |  | 17 | inspect and check for hydraulic system | U17 | 90 | 1M | 52 | bar: W2
UNIFORMITY |  | 18 | inspect and check for all valves | U18 | 90 | 1M | 52 | bar: W2
Visual Machine V1 |  | 1 | inspect and check tension for chain. | I1 | 120 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 2 | inspectand check gear box. | I2 | 360 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 3 | clean and lubracte raches and guides. | I3 | 240 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 4 | check oil level for air lubrcator and gearbox. | I4 | 60 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 5 | checkthe condition of opeation for air cylinders. | I5 | 300 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 6 | check tightness for all bolts and moving parts. | I6 | 240 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 7 | check wear for all all pins an copper bushings. | I7 | 180 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 8 | check and inspect for brakes&drive motor belt. | I8 | 120 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 9 | check the operation of all air solenoide valves. | I9 | 180 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 10 | check the operation of all pnumatic motions(speed). | I10 | 180 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 11 | check for any leakage for air. | I11 | 240 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 12 | check for any leakage for oil. | I12 | 240 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V1 |  | 13 | check for any leakage for greasing. | I13 | 240 | 1M | 10 | bar: W4; W14; W24; W34; W44
Visual Machine V2 |  | 1 | inspect and check tension for chain. | I1 | 120 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 2 | inspectand check gear box. | I2 | 360 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 3 | clean and lubracte raches and guides. | I3 | 240 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 4 | check oil level for air lubrcator and gearbox. | I4 | 60 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 5 | checkthe condition of opeation for air cylinders. | I5 | 300 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 6 | check tightness for all bolts and moving parts. | I6 | 240 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 7 | check wear for all all pins an copper bushings. | I7 | 180 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 8 | check and inspect for brakes&drive motor belt. | I8 | 120 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 9 | check the operation of all air solenoide valves. | I9 | 180 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 10 | check the operation of all pnumatic motions(speed). | I10 | 180 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 11 | check for any leakage for air. | I11 | 240 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 12 | check for any leakage for oil. | I12 | 240 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V2 |  | 13 | check for any leakage for greasing. | I13 | 240 | 1M | 10 | bar: W5; W15; W25; W35; W45
Visual Machine V3 |  | 1 | inspect and check tension for chain. | I1 | 120 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 2 | inspectand check gear box. | I2 | 360 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 3 | clean and lubracte raches and guides. | I3 | 240 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 4 | check oil level for air lubrcator and gearbox. | I4 | 60 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 5 | checkthe condition of opeation for air cylinders. | I5 | 300 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 6 | check tightness for all bolts and moving parts. | I6 | 240 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 7 | check wear for all all pins an copper bushings. | I7 | 180 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 8 | check and inspect for brakes&drive motor belt. | I8 | 120 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 9 | check the operation of all air solenoide valves. | I9 | 180 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 10 | check the operation of all pnumatic motions(speed). | I10 | 180 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 11 | check for any leakage for air. | I11 | 240 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 12 | check for any leakage for oil. | I12 | 240 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V3 |  | 13 | check for any leakage for greasing. | I13 | 240 | 1M | 10 | bar: W6; W16; W26; W36; W46
Visual Machine V4 |  | 1 | inspect and check tension for chain. | I1 | 120 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 2 | inspectand check gear box. | I2 | 360 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 3 | clean and lubracte raches and guides. | I3 | 240 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 4 | check oil level for air lubrcator and gearbox. | I4 | 60 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 5 | checkthe condition of opeation for air cylinders. | I5 | 300 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 6 | check tightness for all bolts and moving parts. | I6 | 240 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 7 | check wear for all all pins an copper bushings. | I7 | 180 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 8 | check and inspect for brakes&drive motor belt. | I8 | 120 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 9 | check the operation of all air solenoide valves. | I9 | 180 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 10 | check the operation of all pnumatic motions(speed). | I10 | 180 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 11 | check for any leakage for air. | I11 | 240 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 12 | check for any leakage for oil. | I12 | 240 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V4 |  | 13 | check for any leakage for greasing. | I13 | 240 | 1M | 10 | bar: W7; W17; W27; W37; W47
Visual Machine V5 |  | 1 | inspect and check tension for chain. | I1 | 120 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 2 | inspectand check gear box. | I2 | 360 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 3 | clean and lubracte raches and guides. | I3 | 240 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 4 | check oil level for air lubrcator and gearbox. | I4 | 60 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 5 | checkthe condition of opeation for air cylinders. | I5 | 300 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 6 | check tightness for all bolts and moving parts. | I6 | 240 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 7 | check wear for all all pins an copper bushings. | I7 | 180 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 8 | check and inspect for brakes&drive motor belt. | I8 | 120 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 9 | check the operation of all air solenoide valves. | I9 | 180 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 10 | check the operation of all pnumatic motions(speed). | I10 | 180 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 11 | check for any leakage for air. | I11 | 240 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 12 | check for any leakage for oil. | I12 | 240 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V5 |  | 13 | check for any leakage for greasing. | I13 | 240 | 1M | 10 | bar: W8; W18; W28; W38; W48
Visual Machine V6 |  | 1 | inspect and check tension for chain. | I1 | 120 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 2 | inspectand check gear box. | I2 | 360 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 3 | clean and lubracte raches and guides. | I3 | 240 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 4 | check oil level for air lubrcator and gearbox. | I4 | 60 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 5 | checkthe condition of opeation for air cylinders. | I5 | 300 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 6 | check tightness for all bolts and moving parts. | I6 | 240 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 7 | check wear for all all pins an copper bushings. | I7 | 180 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 8 | check and inspect for brakes&drive motor belt. | I8 | 120 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 9 | check the operation of all air solenoide valves. | I9 | 180 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 10 | check the operation of all pnumatic motions(speed). | I10 | 180 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 11 | check for any leakage for air. | I11 | 240 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 12 | check for any leakage for oil. | I12 | 240 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V6 |  | 13 | check for any leakage for greasing. | I13 | 240 | 1M | 10 | bar: W9; W19; W29; W39; W49
Visual Machine V7 |  | 1 | inspect and check tension for chain. | I1 | 120 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 2 | inspectand check gear box. | I2 | 360 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 3 | clean and lubracte raches and guides. | I3 | 240 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 4 | check oil level for air lubrcator and gearbox. | I4 | 60 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 5 | checkthe condition of opeation for air cylinders. | I5 | 300 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 6 | check tightness for all bolts and moving parts. | I6 | 240 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 7 | check wear for all all pins an copper bushings. | I7 | 180 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 8 | check and inspect for brakes&drive motor belt. | I8 | 120 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 9 | check the operation of all air solenoide valves. | I9 | 180 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 10 | check the operation of all pnumatic motions(speed). | I10 | 180 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 11 | check for any leakage for air. | I11 | 240 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 12 | check for any leakage for oil. | I12 | 240 | 1M | 10 | bar: W10; W20; W30; W40; W50
Visual Machine V7 |  | 13 | check for any leakage for greasing. | I13 | 240 | 1M | 10 | bar: W10; W20; W30; W40; W50
X-Ray Collman |  | 1 | check air setting (air regulators & filter) | X1 | 60 | 1M | 4 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
X-Ray Collman |  | 2 | check water cooling unit (water pump and level) | X2 | 60 | 1M | 4 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
X-Ray Collman |  | 3 | check spreading device ( grease ball ,screw) | X3 | 30 | 2M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
X-Ray Collman |  | 4 | clean , grease, lub. Diode carriages. | X4 | 60 | 1M | 24 | bar: W1; W25; W49
X-Ray Collman |  | 5 | clean & lub. Holder (tyre holder, R & L ) | X5 | 20 | 1M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
X-Ray Collman |  | 6 | check , clean ,grease all gears,chains | X6 | 10 | 1M | 4 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
X-Ray Collman |  | 7 | check ,clean all roller conveyors. | X7 | 10 | 1M | 4 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
X-Ray Collman |  | 8 | check and inspect air cylinders. | X9 | 10 | 2M | 32 | bar: W1; W33
X-Ray Collman |  | 9 | check tightness for bolts &coupling. | X10 | 10 | 1M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
X-Ray Collman |  | 10 | check pneuamtic system of the operation (solenoid valves). | X9 | 10 | 1M | 32 | bar: W1; W33
X-Ray Collman |  | 11 | check the operation of machine Doors | X11 | 20 | 2M | 8 | bar: W1; W9; W17; W25; W33; W41; W49
X-Ray Collman |  | 12 | check the operation for the mechanism of x-ray tube. | X12 | 60 | 1M | 4 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
X-Ray Collman |  | 13 | check the operation for the mechanism of diode | X13 | 30 | 2M | 4 | bar: W1; W5; W9; W13; W17; W21; W25; W29; W33; W37; W41; W45; W49
X-Ray Collman |  | 14 | check all the sporket gear for wear and its conditions | X14 | 60 | 2M | 16 | bar: W1; W17; W33; W49
X-Ray ALFA |  | 1 | check air setting (air regulators & filter) | X1 | 60 | 1M | 4 | bar: W2; W6; W10; W14; W18; W22; W26; W30; W34; W38; W42; W46; W50
X-Ray ALFA |  | 2 | check water cooling unit (water pump and level) | X2 | 60 | 1M | 4 | bar: W2; W6; W10; W14; W18; W22; W26; W30; W34; W38; W42; W46; W50
X-Ray ALFA |  | 3 | check spreading device ( grease ball ,screw) | X3 | 30 | 2M | 8 | bar: W2; W10; W18; W26; W34; W42; W50
X-Ray ALFA |  | 4 | clean , grease, lub. Diode carriages. | X4 | 60 | 1M | 24 | bar: W2; W26; W50
X-Ray ALFA |  | 5 | clean & lub. Holder (tyre holder, R & L ) | X5 | 20 | 1M | 8 | bar: W2; W10; W18; W26; W34; W42; W50
X-Ray ALFA |  | 6 | check , clean ,grease all gears,chains | X6 | 10 | 1M | 4 | bar: W2; W6; W10; W14; W18; W22; W26; W30; W34; W38; W42; W46; W50
X-Ray ALFA |  | 7 | check ,clean all roller conveyors. | X7 | 10 | 1M | 4 | bar: W2; W6; W10; W14; W18; W22; W26; W30; W34; W38; W42; W46; W50
X-Ray ALFA |  | 8 | check and inspect air cylinders. | X9 | 10 | 2M | 32 | bar: W2; W34
X-Ray ALFA |  | 9 | check tightness for bolts &coupling. | X10 | 10 | 1M | 8 | bar: W2; W10; W18; W26; W34; W42; W50
X-Ray ALFA |  | 10 | check pneuamtic system of the operation (solenoid valves). | X9 | 10 | 1M | 32 | bar: W2; W34
X-Ray ALFA |  | 11 | check the operation of machine Doors | X11 | 20 | 2M | 8 | bar: W2; W10; W18; W26; W34; W42; W50
X-Ray ALFA |  | 12 | check the operation for the mechanism of x-ray tube. | X12 | 60 | 1M | 4 | bar: W2; W6; W10; W14; W18; W22; W26; W30; W34; W38; W42; W46; W50
X-Ray ALFA |  | 13 | check the operation for the mechanism of diode | X13 | 30 | 2M | 4 | bar: W2; W6; W10; W14; W18; W22; W26; W30; W34; W38; W42; W46; W50
X-Ray ALFA |  | 14 | check all the sporket gear for wear and its conditions | X14 | 60 | 2M | 16 | bar: W2; W18; W34; W50
X-Ray MONSANTO |  | 1 | check air setting (air regulators & filter) | X1 | 60 | 1M | 4 | bar: W3; W7; W11; W15; W19; W23; W27; W31; W35; W39; W43; W47; W51
X-Ray MONSANTO |  | 2 | check water cooling unit (water pump and level) | X2 | 60 | 1M | 4 | bar: W3; W7; W11; W15; W19; W23; W27; W31; W35; W39; W43; W47; W51
X-Ray MONSANTO |  | 3 | check spreading device ( grease ball ,screw) | X3 | 30 | 2M | 8 | bar: W3; W11; W19; W27; W35; W43; W51
X-Ray MONSANTO |  | 4 | clean , grease, lub. Diode carriages. | X4 | 60 | 1M | 24 | bar: W3; W27; W51
X-Ray MONSANTO |  | 5 | clean & lub. Holder (tyre holder, R & L ) | X5 | 20 | 1M | 8 | bar: W3; W11; W19; W27; W35; W43; W51
X-Ray MONSANTO |  | 6 | check , clean ,grease all gears,chains | X6 | 10 | 1M | 4 | bar: W3; W7; W11; W15; W19; W23; W27; W31; W35; W39; W43; W47; W51
X-Ray MONSANTO |  | 7 | check ,clean all roller conveyors. | X7 | 10 | 1M | 4 | bar: W3; W7; W11; W15; W19; W23; W27; W31; W35; W39; W43; W47; W51
X-Ray MONSANTO |  | 8 | check and inspect air cylinders. | X9 | 10 | 2M | 32 | bar: W3; W35
X-Ray MONSANTO |  | 9 | check tightness for bolts &coupling. | X10 | 10 | 1M | 8 | bar: W3; W11; W19; W27; W35; W43; W51
X-Ray MONSANTO |  | 10 | check pneuamtic system of the operation (solenoid valves). | X9 | 10 | 1M | 32 | bar: W3; W35
X-Ray MONSANTO |  | 11 | check the operation of machine Doors | X11 | 20 | 2M | 8 | bar: W3; W11; W19; W27; W35; W43; W51
X-Ray MONSANTO |  | 12 | check the operation for the mechanism of x-ray tube. | X12 | 60 | 1M | 4 | bar: W3; W7; W11; W15; W19; W23; W27; W31; W35; W39; W43; W47; W51
X-Ray MONSANTO |  | 13 | check the operation for the mechanism of diode | X13 | 30 | 2M | 4 | bar: W3; W7; W11; W15; W19; W23; W27; W31; W35; W39; W43; W47; W51
X-Ray MONSANTO |  | 14 | check all the sporket gear for wear and its conditions | X14 | 60 | 2M | 16 | bar: W3; W19; W35; W51
ZF Machine | CENTRAL LUBRICATION | 3 | Fluid grease unit : Refill with Shell Gadus S4 V45AC (Alternative: Shell Alvania 1029) | ZF | 30 | 1M | 13 | bar: W12; W25; W38; W51
ZF Machine | CENTRAL LUBRICATION | 6 | Hose lines and connections: Check leak tightness of connections;Check hoses for damage and wear (cracks) | ZF | 30 | 1M | 13 | bar: W12; W25; W38; W51
ZF Machine | LUBRICATION HYDRAULICS | 7 | Pressure settings: Check settings acc. to hydraulic plan | ZF | 90 | 1M | 52 | bar: W52
ZF Machine | LUBRICATION HYDRAULICS | 8 | Filterelement : Check and replace if necessary | ZF | 20 | 1M | 52 | bar: W52
ZF Machine | LUBRICATION HYDRAULICS | 9 | Hose line and connectings: Check leak tightness of connections;Check hoses for damage and wear (cracks) | ZF | 10 | 1M | 26 | bar: W26; W52
ZF Machine | LUBRICATION HYDRAULICS | 10 | Oil Level: Check oil level and quality of oil;Fill with Shell Tellus S2 MX 22 (Alternative: Mobil Velocite No. 10 ISO VG 22) | ZF | 20 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | ELECTRIC COMPONENTS | 12 | Uninterruptible power supply UPS: Check the power supply of the battery acc. to manufacturer specifications | ZF | 30 | 1M | 26 | bar: W26; W52
ZF Machine | ELECTRIC COMPONENTS | 14 | Wiring: Visual inspection of the wiring especially in energy chains and drive connections | ZF | 60 | 1M | 26 | bar: W26; W52
ZF Machine | ELECTRIC COMPONENTS | 15 | Every Emergency stop buttons: Checkfor damage and function | ZF | 60 | 1M | 26 | bar: W26; W52
ZF Machine | In-conveyor roboter-marking unit | 3 | Toothed belt: Clean and replace if necessary | ZF | 30 | 1M | 26 | bar: W26; W52
ZF Machine | COUNTERHOLD | 6 | toothed bar drive: Clean, check for damage and replace if necessary toothed bar, toothed wheel, lubrication wheel | ZF | 30 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | CHANGE ROTATION UNIT | 7 | :Check all units for damage / exceeding wear and loose / missing parts | ZF | 90 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | MANUAL RIM CHANGE MRC | 8 | crane: Check all units for damage / exceeding wear and loose / missing parts | ZF | 20 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | RIM CHANGING TOOL | 9 | tool upper rim: Check all units for damage / exceeding wear and loose / missing parts | ZF | 10 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | RIM CHANGING TOOL | 10 | rim lower rim: Check all units for damage/ exceeding wear and loose/ missing parts | ZF | 20 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | Horizontal carriage Geometry measuring unit | 3 | Ball screw: Clean, check for damage and replace if necessary | ZF | 30 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | Vertical carriage Geometry measuring unit | 6 | Guide carriages and rails: Clean, check for damage and replace if necessary | ZF | 30 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | GEOMETRY MEASURING DEVICE | 7 | Camera unit (Pos. 10): Clean sensor window with glass cleaner or similar; Check sensor, cable connections, and sensor coverage for damage | ZF | 90 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | Carriage drum unit | 8 | Ball screw: Clean, check for damage and replace if necessary | ZF | 20 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | Carriage drum unit | 9 | Guide carriages and rails: Clean, check for damage and replace if necessary | ZF | 10 | 1M | 13 | bar: W12; W25; W38; W51
ZF Machine | DRUM COMPL. | 10 | Load wheel surface (Pos. 200): Clean coated surfaces with dry ice and a brass wire brush or a hard bristle brush to remove rubber residues | ZF | 20 | 1M | 26 | bar: W26; W52
ZF Machine | DRUM COMPL. | 12 | Grease nipple: Grease with Isoflex NBU 15 | ZF | 30 | 1M | 13 | bar: W12; W25; W38; W51
ZF Machine | TROMMELANTRIEB | 14 | Guide carriages and rails: Clean, check for damage and replace if necessary | ZF | 60 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | TROMMELANTRIEB | 15 | friction lining: check for wear and replace if necessary | ZF | 60 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | PUSHER | 16 | :Check all units for damage / exceeding wear and loose / missing parts | ZF | 60 | 1M | 13 | bar: W12; W25; W38; W51
ZF Machine | PUSHER | 17 | Guide carriages and rails: Clean, check for damage and replace if necessary | ZF | 30 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | INTEGR. MEASURE DEV. | 18 | Function: Clean the lens | ZF | 60 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | IN-CONVEYOR | 3 | toothed belt: Clean and replace if necessary | ZF | 30 | 1M | 26 | bar: W26; W52
ZF Machine | LIFTING DEVICE | 6 | : Check for damage and leakage and replace if necessary | ZF | 30 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | LIFTING DEVICE | 7 | Guide carriages and rails: Clean,check for damage and replace if necessary | ZF | 90 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | LIFTING DEVICE | 8 | Toothed bar drive: Clean,check for damage and replace if necessary toothed bar,toothed wheel,lubrication wheel | ZF | 20 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | LIFTING UNIT | 9 | : Clean,check for damage and replace if necessary | ZF | 10 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | LIFTING UNIT | 10 | Guide carriages and rails: Clean,check for damage and replace if necessary | ZF | 20 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | INTERLOCKING | 12 | function: Check radial & axial run-out relating to spindle,contact surfaces to rim & spindle, check damper | ZF | 30 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | BEARING | 14 | Airr outlet of spindle: clean air outlets, replace filter pads | ZF | 60 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | BEARING | 15 | Locking head (Pos.980)and ring (Pos.815): check radial and lateral runout of locking head and ring | ZF | 60 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | BEARING | 16 | Position of pin in ring (Pos. 925): check fixing of pin | ZF | 60 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | BEARING | 17 | Grease nipple (Pos.530)in lower rim fixture (Pos.825): Grease with Shell Gadus | ZF | 30 | 1M | 1 | bar: W1 to W52
ZF Machine | BEARING | 18 | Rim and interlocking system: check snap-in finction | ZF | 60 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | SOAP STATION | 3 | damper:Clean and replace if necessary | ZF | 30 | 1M | 13 | bar: W12; W25; W38; W51
ZF Machine | SOAP STATION | 6 | transmission chains:Clean and replace if necessary | ZF | 30 | 1M | 13 | bar: W12; W25; W38; W51
ZF Machine | SCANNING DEVICE | 7 | Mirror: clean the mirror | ZF | 90 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | SCANNING DEVICE | 8 | Function: Clean the lens | ZF | 20 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | IN-CONVEYOR | 9 | Toothed belt : Clean and replace if necessary | ZF | 10 | 1M | 13 | bar: W12; W25; W38; W51
ZF Machine | IN-CONVEYOR | 10 | Toothed belt disc :Clean and replace if necessary | ZF | 20 | 1M | 26 | bar: W26; W52
ZF Machine | LIFTING UNIT | 12 | Rollers: Clean, check for damage and replace if necessary | ZF | 30 | 1M | 13 | bar: W12; W25; W38; W51
ZF Machine | CENTERING DEVICE | 14 | Guide carriages and rails: Clean, check for damage and replace if necessary | ZF | 60 | 1M | 26 | bar: W26; W52
ZF Machine | CENTERING DEVICE | 15 | Hoses & cables in power track : Clean, check for damage and replace if necessary | ZF | 60 | 1M | 52 | bar: W52
ZF Machine | CENTERING DEVICE | 16 | Roller: Clean, check for damage and replace if necessary | ZF | 60 | 1M | 4 | bar: W4; W8; W12; W16; W20; W24; W28; W32; W36; W40; W44; W48; W52
ZF Machine | SOAPING DEVICE | 17 | Soap coverd surfaces: Remove soap residue,clean components & function check | ZF | 30 | 1M | 1 | bar: W1 to W52
ZF Machine | SOAPING DEVICE | 18 | Brushes: Check condition of bristles and replace brush if necessary | ZF | 60 | 1M | 1 | bar: W1 to W52